## CAPEX SHEDULE (hidden)
Implementation Plan of Major CAPEX
[9 empty] | 0 | 0 | 0
Complex | Power Plant | Description | Estimated Cost for 2024 | Forecasted for 2024 | Revised Estimated cost for 2025 (LKR) | Disbursement during 2025 | Disbursement during 2025 | Disbursement period
|  |  | (LKR) |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2025 |  |  | Total
MC | Victoria | Stator Replacement | 1560000000 | 40% | 1016000000 | 960000000 | 600000000 | [8 empty] | 450000000 |  |  | 510000000 | 600000000 | 960000000 |  | 960000000
|  | Transformer replacement | 680000000 |  |  | 0 | 0 | [13 empty] | 0
|  | Turbine Overhaul | 200000000 |  |  | 0 | 0 | [13 empty] | 0
|  | Penstock pressure relief valve, CT Replacement | 100000000 |  |  | 0 | 0 | [13 empty] | 0 | 960000000
| Kotmale | Circuit Breaker replacement | 130900000 | 90% | 232101000 | 0 | 0 | [13 empty] | 0 | 0 | 0
|  | Unit 1 AVR retrofit | 126990000 |  |  | 0 | 0 | [13 empty] | 0
| Ukuwela | Turbine Head Cover replacement and Spares | 360000000 | 100% | 360000000 | 0 | [14 empty] | 0 |  | 0
| Bowatanna | Procurement of Static Excitation System | 112000000 | 100% | 202000000 | 0 | 0 | [13 empty] | 0 |  | 0
|  | Governor Unit Replacement | 90000000 |  |  | 0 | 0 | [13 empty] | 0 | 11200000
| Randenigala | Rantambe AVR 02 Nos Procurement (80% already paid) | 153000000 | 75% | 182250000 | 0 | 0 | [13 empty] | 0 |  | 0
|  | Major Overhaul | 50000000 |  |  | 0 | 0 | [13 empty] | 0 | 122400000
|  | Drinking Water Treatment Plant | 40000000 |  |  | 0 | 0 | [13 empty] | 0 | 0
| Upper Kotmale | U2 10-year Overhaul (Already Paid) | 282000000 | 100% | 437000000 | 0 | 0 | [13 empty] | 0 |  | 0
|  | Spillway Gates Painting | 35000000 |  |  | 0 | 0 | [13 empty] | 0 | 287250000
|  | Service for 220 kV cable sealing ends | 120000000 |  |  | 0 | 0 | [13 empty] | 0 | 0
| Kothmale Power Station | Replcement of 220 kV circuit breakers (06Nos) | 130900000 | 100% | 243900000 | 0 | 0 | [13 empty] | 0
|  | Retrofit of Excitation sytem of U01 | 113000000 |  |  | 0 | 0 | [13 empty] | 0 | 0
| Other CAPEX works in Mahaweli Complex | Buildings, Office Furniture, Computers, Machinery & Tools, Motor Vehicles, Civil Works etc. | 214740000 | 100% | 214740000 | 0 | 0 | [15 empty] | 0
SC | Samanalawewa | Replacement of 2 Stators | 2270000000 | 60% | 1361000000 | [7 empty] | 227000000 |  |  | 454000000 |  |  |  | 1589000000 | 681000000
|  | Spare parts for Unit 1 Turbine | [5 empty] | 90000000 | 90000000 | [11 empty] | 0 | 936000000
|  | 20 nos. of 132 kV CVTs and 24 nos. of 132 kV CTs | [9 empty] | 35000000 | [5 empty] | 40000000 |  |  | 75000000 | 756000000 | 936000000
| CAPEX works -Hydro Power Station a/c in Samanala Complex |  | 208000000 | 100% | [18 empty] | 0
| Other CAPEX works in Samanala Complex | Buildings, Office Furniture, Computers, Machinery & Tools, Motor Vehicles, Civil Works etc. | 187980000 | 100% | [18 empty] | 0
LC | New Laxapana | Installation of Three (03) Generator Transformers and related works in NLPS | 957000000 | 50% | [16 empty] | 0 |  | 0
| Wimalasurendra | Penstock Exterior Painting - Unit 1 & Unit 2 | 200000000 | 50% | [16 empty] | 0 |  | 0
| CAPEX works in other power plants in Laxapana Complex |  | 332010000 | 80% | [18 empty] | 0
GP | Udawalawa | Installation of 2 Generator Units | 1500000000 | 25%
| LVPP Coal Yard | Enhancing the Coal handling capacity | 6468000000 | [17 empty] | 0
GHQ | CAPEX works in GHQ | Buildings, Office Furniture, Computers, Machinery & Tools, Motor Vehicles, Civil Works etc. | 995000000 | 100% | [16 empty] | 0 |  | 0
LVPP | Overhaul | Level A Maintenance of Unit 1 | 9775000000 | 100% | [16 empty] | 0
|  | Level C Maintenance of Unit 2 & 3 | [18 empty] | 0
| Building Constructions | Workers Apartment Daluwa | 900000000 | 10% | [16 empty] | 0
|  | Coal Yard Extension | 352000000 | 25% | [16 empty] | 0 |  | 0
|  | Construction of Central Sewer Treatment Plant-Daluwa-LV/T/2016/303 | 176000000 | 100% | [16 empty] | 0 | 786850000
|  | Other Building constructions | 452000000 | 75% | [16 empty] | 0
| Other CAPEX works in LVPP | Lands, Office Furniture, Computers, Machinery & Tools, Motor Vehicles, Civil Works etc. | 696000000 | 100% | [16 empty] | 0 | 0
TC | Sapugaskande | Spare parts for E# 01 ; 24,000 rhrs | 500000000 | 100% | [16 empty] | 0 | 856450000
| Sapugaskande | Spare parts for E# 02 ; 12,000 rhrs (2023) | 400000000 | 100% | [16 empty] | 0 | 681450
| Sapugaskande | Spare parts for E# 03 ; 24,000 rhrs (2023) | 500000000 | 100% | [16 empty] | 0 | 0 | 0
| Sapugaskande | Spare parts for major overhauls(12,000 Rhr) 04 Nos of Engines B/F(2023) | 508000000 | 100% | [16 empty] | 0 | 0
| Uthru Jananee | Mechanical Spares for Planned Maintenance for 48000 hrs. maintenance (B/F from year 2023 IND/22/166) | 334740000 | 100% | [16 empty] | 0
| Uthru Jananee | Spare Parts for Watsila Diesel Engings (B/F from 2023- IND/21/354) | 109600000 | 100% | [16 empty] | 0 | 164385000 | 0
| Uthru Jananee | Mechanical Spares for Turbochargers for 48000 hrs. maintenance (B/F from year 2023-IND/23/050 ) | 213200000 | 100% | [16 empty] | 0 | 0
| Barge Mounted Plant | Foreign Purchase Safety Mechanical Spare Parts for All Four Main Engines | 545000000 | [17 empty] | 0 |  | 0
| 1*50 MW Plant | Purchase of 33KV CCV RMU for CSS 1nos and Related spare parts | 183000000 | [17 empty] | 0 |  | 0
| GT 07 | Purchasing of a new Compressor Rotor for GT-07 | 1100000000 | [17 empty] | 0
| GT 07 | Purchase of components of Special maintenance of - GT07 (Extended HGPI)(Forwarded from 2023) | 1293000000 | [17 empty] | 0 |  | 0
| GT 07 | Purchasing of Compressor Diaphragms for GT07 (Forwarded from 2023) | 257000000 | [17 empty] | 0
| GT 07 | Purchasing of Fuel oil Injection Pump | 60000000 | [17 empty] | 0
| GT 07 | Procurement of a new fire water pumping system and fire water boosting system for fuel tank yard | 25000000 | [17 empty] | 0
| GT 07 | Generator Major Inspection including starting group disassembly & Reassembly (B/F) | 45000000 | [17 empty] | 0 | 0
| Combined Circle (KCCP) | New Rotor for GT(B/F 2023) and other related CAPEX developments | 436000000 | 68% | [16 empty] | 0 |  | 0
| KCCP-02 | Battery Banks (220VDC 1 set and UPS 1 set) | 83000000 | 100% | [16 empty] | 0 |  | 0
| Other CAPEX works in Thermal Power Plants | Office Furniture, Computers, Machinery & Tools, Motor Vehicles, Civil Works etc. | 390780000 | 80% | [18 empty] | 0
| Total |  | 36950840000 | 26.28 | 4248991000 | 960000000 | 600000000 | 90000000 | 90000000 | 0 | 0 | 35000000 | 227000000 | 0 | 0 | 904000000 | 0 | 40000000 | 510000000 | 2189000000 |  |  | 1896000000
[10 empty] | 180000000 |  |  | 262000000 |  |  | 904000000 |  |  | 550000000 |  | 1896000000
other capex
[8 empty] | MC |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
[8 empty] | SC |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0
[8 empty] | LC |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
[8 empty] | TC |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
0

## CAPEX SHEDULE (2025 Annex3)
1000000
Annex D
Implementation Plan of Major CAPEX -2025- (With respect to CAPEX plan given in Annex 3)
(To be financed by short term loans)
Complex | Power Plant | Description | Estimated Cost for 2025 | Forecasted for 2024 | Revised Estimated cost for 2024 (LKR) | Disbursement during 2024 | Disbursement during 2025 | Disbursement period
|  |  | (LKR) |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | TOTAL | Jul | Aug | Sep | Oct | Nov | Dec | 2025 | ratio
MC | Victoria | Stator Replacement | 2000000000 |  |  |  |  | 470000000 | 140000000 |  | 400000000 |  |  | 1010000000 | 660000000 |  |  |  | 330000000 |  | 3010000000 | 29.43% | 831 | 4541035000 | 88.26% | #REF!
MC | Victoria | Generator & Penstok | 1020690000 | [9 empty] | 510345000 | 510345000 | [5 empty] | 510345000 | 1531035000 |  | 832 | 184000000 | 3.576% | #REF!
MC | Kotmale | Circuit Breaker replacement | 123000000 | [9 empty] | 61000000 | 61000000 | [5 empty] | 62000000 | 184000000 |  | 838 | 420000000 | 8.163% | #REF!
MC | Upper Kotmale | Consumables,Spillway Gate & 220 kV cable sealing ends | 280000000 | [9 empty] | 140000000 | 140000000 | [5 empty] | 140000000 | 420000000 |  |  | 5145035000 |  | #REF!
SC | Samanalawewa | Replacement of 2 Stators | 1400000000 |  |  |  |  | 470000000 | [5 empty] | 470000000 | 100000000 |  |  |  | 300000000 | 530000000 | 1870000000 | 10.7% | 841 | 1870000000 | 100% | #REF!
GHQ | LVPP Coal Yard | Enhancing the Coal handling capacity | 4000000000 |  |  |  |  | 600000000 | 600000000 | 280000000 | 280000000 | 280000000 | 280000000 | 2320000000 | 280000000 | 280000000 | 280000000 | 280000000 | 280000000 | 280000000 | 6320000000 | 36.15% |  | 1870000000 |  | #REF!
LVPP | LVPP | Expertise Services for Unit 1 Level A Overhaul | 1062000000 | [6 empty] | 1062000000 |  |  |  | 1062000000 | [6 empty] | 2124000000 | 12.15%
LC | New Laxapana | Three (03) Generator Transformers for NLPS | 375000000 | [9 empty] | 75000000 | 75000000 | [5 empty] | 300000000 | 450000000 | 2.574% | 821 | 450000000 | #REF! | #REF!
TC | Sapugaskanda | Purchase of spare parts for E# 01 ; 24,000 rhrs (brought forward from 2024) | 400000000 | [10 empty] | 0 |  | 400000000 |  |  |  |  | 400000000 | 9.008%
TC | Sapugaskanda | Spares for 12,000Rhrs major overhauls of 4 Nos of engines | 350000000 | [10 empty] | 0 |  |  |  | 350000000 |  |  | 350000000
TC | GT 07 | Procurement of a new fire water pumping system and fire water boosting system for fuel tank yard | 350000000 | [9 empty] | 175000000 | 175000000 | [5 empty] | 175000000 | 525000000 |  | 811 | 525000000 | 100% | #REF!
TC | Barge | Hull Inspection and Repair Work | 300000000 | [10 empty] | 0 |  |  |  |  | 300000000 |  | 300000000 |  |  | 525000000 |  | #REF!
| Total |  | 11660690000 | 0 | 0 | 0 | 0 | 1540000000 | 740000000 | 1342000000 | 680000000 | 280000000 | 1241345000 | 5823345000 | 1040000000 | 680000000 | 280000000 | 630000000 | 1210000000 | 1997345000 | 17484035000 | 100%
[8 empty] | 1540000000 | 2280000000 | 3622000000 | 4302000000 | 4582000000 | 5823345000 |  | 6863345000 | 7543345000 | 7823345000 | 8453345000 | 9663345000 | 11660690000

## CAPEX SHEDULE (2025 Other)
1000000
Annex E
Implementation Plan of Major CAPEX -2025- (Other than CAPEX included in Annex 3)
(To be financed by short term loans)
Complex | Power Plant | Description | Estimated Cost for 2025 | Forecasted for 2024 | Revised Estimated cost for 2024 (LKR) | Disbursement during 2024 | Disbursement during 2025 | Disbursement period
|  |  | (LKR) |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | TOTAL | Jul | Aug | Sep | Oct | Nov | Dec | 2025 | ratio
SC | Udawalawa | 5 MVA 6.3/33 kV Transformer for Switchyard & 5 Nos. of 6.3kV CB (Indoor type) | 90000000 | [9 empty] | 45000000 | 45000000 | [5 empty] | 45000000 | 135000000 |  | 845 | 135000000 | #REF! | #REF!
GHQ |  | Major Capex | 506000000 | [9 empty] | 253000000 | 253000000 | [5 empty] | 253000000 | 759000000
LVPP | LVPP | Unit 3 Level B overhaul spares-2026 | 655000000 | [10 empty] | 0 | 210000000 |  | 210000000 |  | 235000000 |  | 655000000
LVPP | LVPP | "A" level maintenance works (Except CMEC works) - Foreign | 576000000 |  |  |  |  | 288000000 | 288000000 |  |  |  |  | 576000000 | [6 empty] | 1152000000
LVPP | LVPP | Level B spares | 400000000 | [9 empty] | 100000000 | 100000000 | 200000000 | 100000000 |  |  |  |  | 500000000
LVPP | LVPP | Expertise Services for Unit 2 Level B Overhaul | 596000000 | [10 empty] | 0 |  | 238400000 |  |  |  | 357600000 | 596000000
LVPP | LVPP | Other Coal Power related CAPEX | 1150000000 |  |  |  |  | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 575000000 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 95833333.3333 | 1725000000
LVPP | LVPP | Security Improvements | 100000000 | [6 empty] | 50000000 |  |  |  | 50000000 | 50000000 | [5 empty] | 150000000
LVPP | LVPP | Other majour capex | 1562630000 | [6 empty] | 390657500 |  |  | 390657500 | 781315000 |  |  | 390657500 |  |  | 390657500 | 2343945000
LC | New Laxapana | Two (02) new conventional runners for NLPS | 180000000 | [10 empty] | 0 |  | 180000000 |  |  |  |  | 180000000 |  | 822 | 525000000 | 100% | #REF!
LC | New Laxapana | 12 Circuit Breakers for OLPS and NLPS Switchyards (132 kV) | 110000000 | [9 empty] | 22000000 | 22000000 | [5 empty] | 88000000 | 132000000 |  |  | 525000000 |  | #REF!
LC | Samanala | Spare parts for Generators & Turbines (Foreign) | 350000000 | [9 empty] | 175000000 | 175000000 | [5 empty] | 175000000 | 525000000
TC | Sapugaskanda | Purchase of spare parts for E# 04 ; 24,000 rhrs | 400000000 | [10 empty] | 0 |  |  |  | 400000000 |  |  | 400000000
TC | Sapugaskanda | Purchase of 2 Nos of FOCs for Station A | 100000000 | [9 empty] | 50000000 | 50000000 | [5 empty] | 50000000 | 150000000 |  | 813 | 550000000 | 23.39% | #REF!
TC | Uthru Jananee | Mechanical Spares for Boilers &PLC Upgrade | 251000000 | [9 empty] | 125500000 | 125500000 | [5 empty] | 125500000 | 376500000 |  | 816 | 376500000 | 16.01% | #REF!
TC | Barge | Hull Inspection,Safety Mechanical Spare Parts for All Four Main Engines,Repair Work of Stacks & Generator of DG #3 | 400000000 | [6 empty] | 100000000 |  |  | 100000000 | 200000000 |  |  | 100000000 |  |  | 100000000 | 600000000 |  | 817 | 900000000 | 38.27% | #REF!
TC | KCCP | DCS Upgrade | 240000000 | [9 empty] | 120000000 | 120000000 | [5 empty] | 120000000 | 360000000 |  | 812 | 360000000 | 15.31% | #REF!
TC | KCCP-02 | Replacement of Pro-Control system including SCADA system | 110000000 | [9 empty] | 55000000 | 55000000 | [5 empty] | 55000000 | 165000000 |  | 819 | 165000000 | 7.017% | #REF!
TC | Barge | Hull Inspection and Repair Work | 300000000 | [10 empty] | 0 |  |  |  |  | 300000000 |  | 300000000 |  |  | 2351500000 |  | #REF!
| Total |  | 8076630000 | 0 | 0 | 0 | 0 | 383833333.3333 | 383833333.3333 | 636490833.3333 | 95833333.3333 | 95833333.3333 | 1531990833.3333 | 3127815000 | 555833333.3333 | 614233333.3333 | 796490833.3333 | 495833333.3333 | 630833333.3333 | 1855590833.3333 | 11204445000 | 0%
[8 empty] | 383833333.3333 | 767666666.6667 | 1404157500 | 1499990833.3333 | 1595824166.6667 | 3127815000 |  | 3683648333.3333 | 4297881666.6667 | 5094372500 | 5590205833.3333 | 6221039166.6667 | 8076630000
Implementation Plan of Major CAPEX -2025- (Other than CAPEX included in Annex 3)
| Other Capex | (CEB own funds will be used)
Mahaweli Complex | Victoria | Other Hydro related CAPEX | [5 empty] | 2472078.5 | 2472078.5 | 2472078.5 | 2472078.5 | 2472078.5 | 2472078.5 | 14832471
| Kotmale | [6 empty] | 13433181.1667 | 13433181.1667 | 13433181.1667 | 13433181.1667 | 13433181.1667 | 13433181.1667 | 80599087
| U.Kotmale | [6 empty] | 1146084.9167 | 1146084.9167 | 1146084.9167 | 1146084.9167 | 1146084.9167 | 1146084.9167 | 6876509.5
| Ukuwela | [6 empty] | 1199391.1667 | 1199391.1667 | 1199391.1667 | 1199391.1667 | 1199391.1667 | 1199391.1667 | 7196347
| Bowatenna | [6 empty] | 1066125.5 | 1066125.5 | 1066125.5 | 1066125.5 | 1066125.5 | 1066125.5 | 6396753
| Rand/Rant | [6 empty] | 4750921.6667 | 4750921.6667 | 4750921.6667 | 4750921.6667 | 4750921.6667 | 4750921.6667 | 28505530
| Nilambe | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thambapavani | [6 empty] | 2198883.8333 | 2198883.8333 | 2198883.8333 | 2198883.8333 | 2198883.8333 | 2198883.8333 | 13193303
Samanala Complex | SWPS | Other Hydro related CAPEX | [5 empty] | 4421703.3333 | 4421703.3333 | 4421703.3333 | 4421703.3333 | 4421703.3333 | 4421703.3333 | 26530220
| Kukule | [6 empty] | 5414518.1667 | 5414518.1667 | 5414518.1667 | 5414518.1667 | 5414518.1667 | 5414518.1667 | 32487109
| Umaoya | [6 empty] | 12127049.8333 | 12127049.8333 | 12127049.8333 | 12127049.8333 | 12127049.8333 | 12127049.8333 | 72762299
| IPS | [6 empty] | 4136728.6667 | 4136728.6667 | 4136728.6667 | 4136728.6667 | 4136728.6667 | 4136728.6667 | 24820372
| UPS | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laxapana Complex | O-N Laxa | Other Hydro related CAPEX | [5 empty] | 14085349.5 | 14085349.5 | 14085349.5 | 14085349.5 | 14085349.5 | 14085349.5 | 84512097
| Polpitiya | [6 empty] | 1449738 | 1449738 | 1449738 | 1449738 | 1449738 | 1449738 | 8698428
| WPS | [6 empty] | 7355512.9167 | 7355512.9167 | 7355512.9167 | 7355512.9167 | 7355512.9167 | 7355512.9167 | 44133077.5
| Canyon | [6 empty] | 3418329.6667 | 3418329.6667 | 3418329.6667 | 3418329.6667 | 3418329.6667 | 3418329.6667 | 20509978
| Broadland | [6 empty] | 7720236.5 | 7720236.5 | 7720236.5 | 7720236.5 | 7720236.5 | 7720236.5 | 46321419
Thermal Complex | KPS | Other CAPEX works in Thermal Power Plants | [5 empty] | 4749672.7292 | 4749672.7292 | 4749672.7292 | 4749672.7292 | 4749672.7292 | 4749672.7292 | 28498036.375
| KCCP | [6 empty] | 4540719.2758 | 4540719.2758 | 4540719.2758 | 4540719.2758 | 4540719.2758 | 4540719.2758 | 27244315.655
| KCCP 2 | [6 empty] | 2941421.69 | 2941421.69 | 2941421.69 | 2941421.69 | 2941421.69 | 2941421.69 | 17648530.14
| Sapu | [6 empty] | 2284710.8367 | 2284710.8367 | 2284710.8367 | 2284710.8367 | 2284710.8367 | 2284710.8367 | 13708265.02
| Uthuru Janani | [6 empty] | 2183333.9692 | 2183333.9692 | 2183333.9692 | 2183333.9692 | 2183333.9692 | 2183333.9692 | 13100003.815
| Barge | [6 empty] | 184269.3917 | 184269.3917 | 184269.3917 | 184269.3917 | 184269.3917 | 184269.3917 | 1105616.35
| Chunnakam | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 50 MW | [6 empty] | 1182538.775 | 1182538.775 | 1182538.775 | 1182538.775 | 1182538.775 | 1182538.775 | 7095232.65
LVPP | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
GHQ | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL | [5 empty] | 104462500.0008 | 104462500.0008 | 104462500.0008 | 104462500.0008 | 104462500.0008 | 104462500.0008 | 626775000.005